## Project Charter
PROJECT CHARTER
Project Title | [5 empty] | Date | 2021-12-03
Opportunity
Goals
Deliverables
Project Scope
Stakeholders
Project Start Date |  |  | Project Leader
Project Conclusion Date |  |  | Sponsor
Estimated Budget
Notes:
Team Members
Constraints
Milestones |  | 1 |  |  | 4
|  | 2 |  |  | 5
|  | 3 |  |  | 6
Important requirements
Risk Mitigation
Communication Plan
Refereces (previous projects)
Key Suppliers, Anexos (ex. desenhos)
Norms
João Paulo Pinto, 2015 ©

## Scrumboard
W E L C O M E T O T H E S C R U M B O A R D
STORIES (US) | TO DO | IN PROGRESS | TESTING | DONE
João Paulo Pinto, 2016 July - CLT Valuebased Services

## Burndown
T H E S P R I N T B U R N D O W N C H A R T
Project Title |  | Projecto Scrum Infosystem | Sprint Identification |  | S07 |  | Current Day | 2021-12-03 |  | Dias realizados |  | 25
Scrum Master |  | Christiane Tscharf | Total Sprint Backlog |  | 450 | hrs | Average Work / Day | 18 | hrs | Média do trabalho |  | 18
[10 empty] | Dias em atraso |  | 0
Work in Progress
Day | Done | Accum | [7 empty] | Dados para o gráfico:
1 | 0 | 0 | [8 empty] | Day | Planeado | Atual
2 | 14 | 14 | [8 empty] | 1 | 432 | 450
3 | 22 | 36 | [8 empty] | 2 | 414 | 436
4 | 5 | 41 | [8 empty] | 3 | 396 | 414
5 | 5 | 46 | [8 empty] | 4 | 378 | 409
6 | 2 | 48 | [8 empty] | 5 | 360 | 404
7 | 25 | 73 | [8 empty] | 6 | 342 | 402
8 | 20 | 93 | [8 empty] | 7 | 324 | 377
9 | 0 | 93 | [8 empty] | 8 | 306 | 357
10 | 15 | 108 | [8 empty] | 9 | 288 | 357
11 | 30 | 138 | [8 empty] | 10 | 270 | 342
12 | 5 | 143 | [8 empty] | 11 | 252 | 312
13 | 0 | 143 | [8 empty] | 12 | 234 | 307
14 | 0 | 143 | [8 empty] | 13 | 216 | 307
15 | 5 | 148 | [8 empty] | 14 | 198 | 307
16 | 35 | 183 | [8 empty] | 15 | 180 | 302
17 | 25 | 208 | [8 empty] | 16 | 162 | 267
18 | 25 | 233 | [8 empty] | 17 | 144 | 242
19 | 40 | 273 | [8 empty] | 18 | 126 | 217
20 | 50 | 323 | [8 empty] | 19 | 108 | 177
21 | 65 | 388 | [8 empty] | 20 | 90 | 127
22 | 5 | 393 | [8 empty] | 21 | 72 | 62
23 | 25 | 418 | [8 empty] | 22 | 54 | 57
24 | 3 | 421 | [8 empty] | 23 | 36 | 32
25 | 29 | 450 | Expected Sprint Delay | 0 | days | [5 empty] | 24 | 18 | 29
[11 empty] | 25 | 0 | 0
CLT VALUEBASED SERVICES Lda | [8 empty] | SCRUM MASTER CERTIFICATION - 2018/19 ©

## A3 - AAR
A3. A F T E R A C T I O N R E P O R T
Project |  |  | Code | Date | 2021-12-03
Leader |  | Observations
PROJECT'S SUMMARY |  |  | ANALYSIS OF CRITICAL TASKS
r
ANALYSIS OF RESULTS AND LESSONS LEARNT |  |  | RECOMENDATIONS
| Company Name here |  |  |  |  | JOAO PAULO PINTO © 2015